## Sheet1
PRODUCT BACKLOG FOR AREO.NET
ID | As a... | I want to be able to... | So that.... | Priority | Sprint | Status
1 | Customer | View List of all Customers and Plan | I can monitercustomer & plan usage | Must | 1 | Working in progress
2 | Customer | Update Customer Details | be contacted by Supplier/Administrator | Must | 1 | Done
3 | Customer | Add New Customer | allow new membes to engage and join plan | Must | 1 | Done
4 | Customer | Fetch Customer by Customer ID | select required Customer and view selecte details | Must |  | Done
5 | Customer | Fetch Customer by ID Proof | select required Customer and view selecte details | Could |  | Done
6 | Plan | View List of all Plan | moniter all plan | Must |  | Done
7 | Plan | Add new Plan | Introduce new stratagic plan to customers | Must |  | Done
8 | Plan | Update Existing Plant | Change required section in existing plan | Must |  | Done
9 | Plan | Fetch Plan by Plan ID | select and view required plan details | Must |  | Done
10 | Plan | Fetch Plan by Plan Name | select and view required plan details | Could |  | Done
11 | Call Details | Fetch all Users call histrory |  |  |  | To be started
12 | Call Details | Fetch Customer by Call ID |  |  |  | To be started
13 | Call Details | Fetch Customer by Call duration |  |  |  | To be started
14 | Call Details | Find Call duration of requested Customer |  |  |  | To be started
15 | Call Details | Find Amount charged for each Call |  |  |  | To be started
16 | Call Details | Find Plan Validity for each Customer |  |  |  | To be started